## Sheet1
Task Name | Deadline | Responsible People | Sprint Ready | Priority | Status | Story Points | Deliverables | Description
Sprint 1 (Intital research) | 2019-03-14 | [5 empty] | 2019-02-25 | Choose a project proposal and send your choice via email to epsatisep@gmail.com
Initial Research: electronics Research principle Research competition analysis |  | Pascal & Elisa Marie & Dániel João & Nacho |  |  | in Progress |  | 2019-03-06 | Define the Project Backlog (what must be done and key deliverables - every member should preferably participate in every task), Global Sprint Plan, Initial Sprint Plan (which tasks should be included, who does what) and Release Gantt Chart of the project and insert them on the wiki (planning)
[7 empty] | 2019-03-11 | Upload the “black box” System Diagrams & Structural Drafts to the wiki
Communication & Marketing task: Defining the target group Field Indentification |  | whole group |  |  | Done |  | 2019-03-22 | Upload the detailed System Schematics & Structural Drawings to the wiki and do the cardboard scale model of the structure
Project management task: Creating this Backlog & these Sprints |  | Pascal (till now) |  |  | in Progress |  | 2019-03-27 | Upload the List of Materials (what & quantity) to the wiki
Sponge Experiment: gathering materials, setting up & measuring |  | Joao |  |  | not done |  | 2019-04-06 | Upload the Interim Report and Presentation to the wiki. The report must contain the the following chapters: Introduction, Project Management, State of the Art, Marketing Plan, Project Management, Eco-eficiency Measures for Sustainability, Ethical and Deontological Concerns, Proposed Solution and Bibliography. The Project Management chapter includes the updated project progress register, the sprint report for completed sprints (tasks that were included, statuses, assignees, allocations) and the updated release Gantt chart
Sprint 2 | [6 empty] | 2019-04-11 | Interim Presentation, Discussion and Peer, Teacher and Supervisor Feedbacks
[7 empty] | 2019-04-23 | Complete the List of Materials (local providers & price, including VAT and transportation) to the wiki
[7 empty] | 2019-05-30 | Upload refined Interim Report (based on Teacher & Supervisor Feedbacks)
[7 empty] | 2019-06-03 | Upload the results of the Functional Tests to the wiki
Sprint 3 | [6 empty] | 2019-06-14 | Upload the Final Report, Presentation, Video, Paper, Poster and Manual
[7 empty] | 2019-06-19 | Final Presentation, Individual Discussion and Assessment
[7 empty] | 2019-06-25 | 1. Update the wiki, report, paper with all correction suggestions
2. Hand in to the EPS coordinator:
I. a CD with the corrected deliverables (source + PDF) together with all code and drawings produced
Sprint 4 | [7 empty] | II. a printed copy of the corrected report and poster